## Sheet1
Date | Hours | Completed
2014-10-17 | 1 | Setup Xcode, and setup TestFlight
2014-10-18
2014-10-19
2014-10-20
2014-10-21 | 2 | Add Parse.com and setup the anonymous user. Set the correct device size
2014-10-22 | 4.5 | Add include assistant view. Incline UIView is not good enough, looks ok. Add UITapGestureRecognizer to AssistantView. Add four touch delegate. Add Up and down views, including setuping NewsTableViewController
2014-10-23 | 2.5 | Load data from Parse.com and display them on the ArticlesTableViewController. Build VoiceImagesManager to handle image
2014-10-24 | 3 | Add ArticleTableViewCell
2014-10-25 | 3.5 | Load images into Photo Wall. Setup the backend for ads. Add AdsManager to handle loading from Parse.om
2014-10-26
2014-10-27 | 3.5 | Setup view and view navigation. Ad System TableViewCell_s are ready now.
2014-10-28 | 0.5 | Setup A/B testing
2014-10-29 | 1.5 | Setup Mixpanel to track users' behaviour.
2014-10-30 | 0.5 | Working on backend on Parse.com
2014-10-31 | 3 | Load ads into the article successfully.
2014-11-01 | 1 | Found a bug in Collection view and reloved it.
2014-11-02
2014-11-03 | 1.5 | Load text paragraph.
2014-11-04 | 1 | Update backend. No articleDetail class anymore.
2014-11-05 | 0.5 | Removed A/B Testing method.
2014-11-06 | 0.5 | Add launch gif.
2014-11-07 | 3 | Reduce GPU computation when loading GIF. Create VoicePFImage to handle image loading. AssistantHorizontalView works now.
2014-11-08 | 4 | Update backend to store more images. Button on AssistantHorizontalView works now.
2014-11-09 | 2 | Update cover image. Update paragraphes.
2014-11-10 | 1 | Update UI and animation of the assistant view.
2014-11-11 | 0
2014-11-12 | 0
2014-11-13 | 0
2014-11-14 | 0
2014-11-15 | 0
2014-11-16 | 1 | Update street images class. Setup the relation between several views.
2014-11-17 | 0
2014-11-18 | 0
2014-11-19 | 0
2014-11-20 | 0.5 | Add StreetDetailViewController
2014-11-21 | 0.5 | Update UI and Animation
2014-11-22 | 0
2014-11-23 | 2 | Load multiply images on the screen.
2014-11-24 | 0.5 | Add progress indicator.
2014-11-25
44.5